## Test Scenarios
c
Project Name | https://evaly.com.bd/
Reference Document | FRS
Created By | Humaira Gulshan Putul
Creation Date | 30-12-2023
Approval Date | 2024-01-01
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Sign Up" functionality | P1 | 31
TS_004 |  | Validate the working of the "Sign In" functionality. | P0 | 14
TS_006 |  | Validate the working of "Header" functionality. | P1 | 10
TS_006 |  | Validate the working of " Home Page Elements" functionality. | P3 | 47
TS_009 |  | Validate the working of "Footer" functionality. | P4 | 7
TS_010 |  | Validate the working of "Search Bar" functionality. | P4 | 1
TS_012 |  | Validate the working of "Gadget Fest" functionality. | P5 | 1
TS_013 |  | Validate the working of "Get offer" functionality. | P5 | 5
TS_014 |  | Validate the working of "OTP" functionality. | P1 | 5
TS_015 |  | Validate the working of "Forgotten Password?" functionality. | P2 | 10
TS_016 |  | Validate the working of "Mobile Deal" functionality. | P3 | 1
TS_017 |  | Validate the working of "PC Builder" functionality. | P3 | 1
TS_018 |  | Validate the working of "accessories"functionality. | P4 | 1
TS_019 |  | Validate the working of "office-equipment" functionality. | P5 | 1
TS_020 |  | Validate the working of "SUPPORT"functionality. | P5 | 1

## Test Cases
Product Name |  | https://evaly.com.bd/ | TC Start Date | 26/12/2023 | TC Execution Start Date | 2024-01-01 |  |  |  |  | TEST CASE
Module Name |  | User Management, Header, Home page Elements,Footer | TC End Date | 2023-05-12 | TC Execution End Date | 2024-08-01 |  |  |  |  | PASS | 127
Epic |  |  | Test Case Developed By | Humaira Gulshan Putul | Browser (tested) | Yes |  |  |  |  | FAIL | 14
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 141
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Mozilla Firefox Microsoft Edge | 1. Goto different browsers 2. Search 'Evaly Shop' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/ 2. Click on sign in button at the right corner 3. Click on sign up 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per requirements | N/A | 1. Goto the URL https://evaly.com.bd/ 2. Click on sign in button at the right corner 3. Click on sign up 3. Check the fonts,text color and style |  |  | Passed
4 |  |  |  | Ensuring capitalization for each field | n should be capital of the Full Name and also p should be capital of the Confirm Password | Not Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check the fields | SS\n_p_should_be_N_P.PNG |  | Failed
5 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be presented | Not Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check asterisk beside mandatory fields | SS\Red_asterisk_Sign_up.PNG |  | Failed
6 |  |  |  | Checking password can copy to the confirm password | Should not be copied | Found as per expectation | Password: john@88 | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check password can copy to the confirm password field |  |  | Passed
7 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should present | Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check the alignments of the fields |  |  | Passed
8 |  |  |  | eye icon for password field | Eye icon should present at the password field | Not Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check the eye icon in the password field |  |  | Failed
9 |  |  |  | Checking 'Remember Me' checkbox | Should present | Not found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check remember me checkbox |  |  | Failed
10 |  | Functional Testing |  | Keeping mandatory fields blank | Should not allow user to register | Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Keep mandatory fields blank 3.Click create account |  |  | Passed
11 |  |  |  | Verifying Full Name | Should not accept only blank spaces | Not Found as per expectation | Full Name : (Blank spaces) | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Put blank spaces in the Full name field |  |  | Failed
12 |  |  |  | Entering blank at first position in the name field | Should not accept the provided input | Not Found as per expectation | Aakk kkhhQQ | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Put blank spaces at the first position of the name in the Full name field | SS\Blank_Spaces.PNG |  | Failed
13 |  |  |  | Entering blank at last position of full name | Should not accept the provided input | Not found as per expectation | BBggn qgKnnj | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Put blank spaces at the last position of the name in the Full name field | SS\Blank_Spaces_L_Position.PNG |  | Failed
14 |  |  |  | Verifying error messages for input fields | Error message should be "enter your full name" for the Full Name field | Not Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check the error message of full name field | SS\Full_Name.PNG |  | Failed
15 |  |  |  | Inputing full name with only special characters | Should not accept the provided input | Not found as per expectation | *&&&*()))) **###@%% | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Input Special characters in the name field | SS\Special_Char.PNG |  | Failed
16 |  |  |  | Inputing full name with only numbers | Should not accept the provided input | Not found as per expectation | 66754455 7589699 | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Input numbers in the name field | SS\Number.PNG |  | Failed
17 |  |  |  | Inputing full name with decimal numbers | Should not accept the provided input | Not found as per expectation | 78.7568.99 87.9878.4 | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Input numbers in the name field | SS\decimal.PNG |  | Failed
18 |  |  |  | Inputing full name with alphabets | Should accept the provided input | Found as per expectation | John Austin | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Input alphabets |  |  | Passed
19 |  |  |  | Entering comma between alphabets for full name | Should not accept the provided input | Not found as per expectation | jjs,iioo jjdh,dhu | 1. Goto the URL https://evaly.com.bd/auth/signup 2.Input alphabets with comma | SS\Comma_between.PNG |  | Failed
20 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | humairagulshan2807@gmail.com | 1. Goto the URL https://evaly.com.bd/auth/signup 2. Fill the email address with already registered email |  |  | Passed
21 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation with an error message | fggggj2@gghgh | 1.Goto the URL https://evaly.com.bd/auth/signup 2. Fill the email address with invalid email address format |  |  | Passed
22 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | abc@gmail.com | 1.Goto the URL https://evaly.com.bd/auth/signup 2. Fill the email address with valid email address format |  |  | Passed
23 |  |  |  | Checking password and confirm field values are masked | Should be masked | Found as per expectation | abc8888 | 1.Goto the URL https://evaly.com.bd/auth/signup 2. Enter password and confirm password |  |  | Passed
24 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Found as per expectation | abc8889 | 1.Goto the URL https://evaly.com.bd/auth/signup 2.Enter invalid combinations of characters in password and confirm password |  |  | Passed
25 |  |  |  | Inputing weak password length | Should not allow user to register | Found as per expectation | hhg#k88 | 1.Goto the URL https://evaly.com.bd/auth/signup 2.Enter weak password length in password and confirm password |  |  | Passed
26 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | hgjkgjkjkjh!&*77 | 1.Goto the URL https://evaly.com.bd/auth/signup 2.Enter strong password length in password and confirm password |  |  | Passed
27 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | Password: john@8888 Confirm password: jnn8888 | 1.Goto the URL https://evaly.com.bd/auth/signup 2.Enter different values in password and confirm password |  |  | Passed
28 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | Password: john@8888 Confirm password: john@8888 | 1.Goto the URL https://evaly.com.bd/auth/signup 2.Enter same values in password and confirm password |  |  | Passed
29 |  |  |  | Checking create account button with valid credentials | Should allow user to register | Found as per expectation | Full Name : Humaira Email:humairagulshan2807@gmail.com Password:1234567@ Confirm Password:1234567@ | 1.Goto the URL https://evaly.com.bd/auth/signup 2. Fill all the fiels with valid credentials 3.Click 'Create an Account' |  |  | Passed
30 |  |  |  | Checking email verification OTP sent to the registered email | Sent successfully | Found as per expectation | Full Name : Humaira Email:humairagulshan2807@gmail.com Password:1234567@ Confirm Password:1234567@ | 1.Goto the URL https://evaly.com.bd/auth/signup 2. Fill all the fiels with valid credentials 3.Click 'Create an Account' |  |  | Passed
31 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | jane9999 | 1.Goto the URL https://evaly.com.bd/auth/signup 2. Copy paste text in every field |  |  | Passed
32 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1.Goto the URL https://evaly.com.bd/auth/signup 3. Enter enter in every field |  |  | Passed
33 |  | Functionality Testing | Sign In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/login 2. Keep both the fields blank |  |  | Passed
34 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | john@8888 | 1. Goto the URL https://evaly.com.bd/auth/login 2. Input values in password field and check if it is masked |  |  | Passed
35 |  |  |  | Checking sign in with google account | Should allow user to sign in | Found as per expectation | N/A | 1. Go to the URL https://evaly.com.bd/auth/login 2.Click sign in with google |  |  | Passed
36 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | fgcfh@nndj.com hdjui44 | 1. Goto the URL https://evaly.com.bd/auth/login 2. Input invalid credentials in email and password field |  |  | Passed
37 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | Email: humairagulshan2807@gmail.com Password: 1234567@ | 1. Goto the URL https://evaly.com.bd/auth/login 2. Input valid credentials in email and password field |  |  | Passed
38 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for managing sign in | Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/login 2.Click on 'Forgot Password' 3. Check email |  |  | Passed | Should be able to reset the password not only facilitate to sign in with one time password
39 |  |  |  | Verifying forgot password reply email is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/login 2.Enter Email 3.Click on 'Forgot Password' 4. Check the registered email |  |  | Passed
40 |  |  |  | Checking Reset password | Should provide a functionality to reset password | There is no functionality to reset the password | N/A | 1. Goto the URL https://evaly.com.bd/auth/login 2.Enter Email 3.Click on 'Forgot Password' | SS\No_Reset_pass.PNG |  | Failed
41 |  |  |  | Verifying login with the newly sent one time password | Should allow user to login | Found as per expectation | Email: janev4141@gmail.com Password: jane@4444 | 1. Goto the URL https://evaly.com.bd/auth/login 2.Input registered Email 3.Click on 'Forgot Password' 4. Check the registered email 5.Input new one time password 6. Click on login |  |  | Passed
42 |  |  |  | Checking lifetime of the one time password | Should not allow user to login by using the one time password after 10 minitues | Found as per expectation | Email:humairagulshan2807@gmail.com One Time Password:200458 | 1. Goto the URL https://evaly.com.bd/auth/login 2.Input registered Email 3.Click on 'Forgot Password' 4. Check the registered email 5.Input the given OTP after 10 minitues 6. Click on login |  |  | passed
43 |  | UI Testing | Sign In | Checking Spelling and grammar mistakes | Should not found any grammar or spelling mistakes | Found as per expection | N/A | 1. Goto the URL https://evaly.com.bd/auth/login 2.Check spelling and grammar mistakes |  |  | Passed
44 |  |  |  | Verifying the font, text color and style | Should as per requirements | Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/login 2.Check the color,text, fonts and style |  |  | Passed
45 |  |  |  | Verifying mandatory field is marked with a red asterisk | Should present the asterisk sign | Not Found as per expectation | N/A | 1. Goto the URL https://evaly.com.bd/auth/login 2.Check mandatory fields have red asterisk | SS\Red_asterisk_Login.PNG |  | Failed
46 |  |  |  | Checking alignments of the fields | Should found as per requirements | Found as per requirements | N/A | 1. Goto the URL https://evaly.com.bd/auth/login 2.Check the alignments of the fields |  |  | Passed
47 | Header | Functionality Testing | Search | Verifying search functionality for accurate and relevant results | Should found as per expectation | Found as per expectation | Example:Dresses Shoes etc | 1.Go to the URL https://evaly.com.bd/ 2.Search any products from search bar |  |  | Passed
48 |  |  | Add to Cart | Checking user can navigate add to cart easily | User should be able to navigate the add to cart easily | Found as per expectation | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Navigate add to cart |  |  | Passed
49 |  |  | Home | Checking home can navigate correctly | Should found as per expectation | Found as per expectation | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Navigate Home option |  |  | Passed
50 |  |  | Shops | Checking navigation to shops directs to the correct page | Should found as per expectation | Found as per expectation | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Navigate Shops option |  |  | Passed
51 |  |  | Categories | Verifying navigation to categories directs to the correct page | Should be navigated properly | Found as per expectation | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Navigate Categories option |  |  | Passed
52 |  | UI Testing |  | Checking spelling and grammatical mistakes | Should not found any spelling or grammatical mistake. | Found as per expectation | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check spelling and grammars of the Header section |  |  | Passed
53 |  |  |  | Checking the fonts, style and color of the text | Should as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the fonts, style and colors of the header section |  |  | Passed
54 |  |  |  | Checking all the icons placed correctly | Should as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the icons |  |  | Passed
55 |  |  |  | Checking "search in Evaly" text is present as a placeholder in the search box | Should present | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the search box |  |  | Passed
56 |  |  |  | Verifying the icon filled with black when cursor placed over it | Should filled with black | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the icons of home, shops and categories |  |  | Passed
57 | Home Page Elements | Functional Testing | Slider | Ensure that the slider moves according to the click input of the dot buttons | Should move as per expectation | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check the slider position after mouse clicks |  |  | Passed
58 |  |  |  | Verify that user is directed to the relevant shop page after clicking the slider | Should direct the user to the Shops page | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Click the slider and notice the directed page |  |  | Passed
59 |  |  | Flash Sale Products | Verifying user can navigate products from home page of the Flash Sale section | Should be able to navigate product | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click a product |  |  | Passed
60 |  |  |  | Verifying show more button of products section directs the user to product page to view more | Should allow the user to view more | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click show more button |  |  | Passed
61 |  |  |  | Verifying the side arrows button of products section works perfectly | Should work perfectly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click side arrows of products section |  |  | Passed
62 |  |  | Shops | Verifying the side arrows button of shops section works perfectly | Should work perfectly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click side arrows of shops section |  |  | Passed
63 |  |  |  | Verify that Shops can be navigated from Shops section of the home page | User should able to navigate | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click a shop from shops section |  |  | Passed
64 |  |  | Deals of the Day | Checking Deals of the day section's product can navigate perfectly | Should be navigated correctly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click a product from deals of the day |  |  | Passed
65 |  |  | Trending Now | Verify that products can be navigated from Trendig Now section of the home page | User should able to navigate | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click a product from Trending Now |  |  | Passed
66 |  |  | Popular Products | Check that products can be navigated from Popular Products section | Should be navigated properly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click a product from popular products |  |  | Passed
67 |  |  | Top Rated Shops | Verifying shops can be navigated from Top Rated Shops | Should be navigated | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click a shop from Top Rated Shops |  |  | Passed
68 |  |  |  | Checking that side arrows of Top Rated Shops works perfectly | Should allow user to see more products | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click the side arrow of the Top Rated Shops |  |  | Passed
69 |  |  | COD | Checking COD section's shops can be navigated perfectly | Should as per expectations | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click any shop from the COD section |  |  | Passed
70 |  |  |  | Check that show more button of the COD section directs the user to the shops page | Should direct the user to the Shops page | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click show more button |  |  | Passed
70 |  |  |  | Checking side arrows of the COD section works perfectly | Should work perfectly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check side arrows of the COD section |  |  | Passed
71 |  |  | B2B | Check that B2B section can be navigated perfectly | Should be navigated correctly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click a shop from B2B section |  |  | Passed
72 |  |  |  | Check that show more button of the B2B section directs the user to the shops page | Should direct the user to the Shops page | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click show more button from B2B section |  |  | Passed
73 |  |  |  | Checking that side arrows of B2B works perfectly | should work correctly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check side arrows of the B2B section |  |  | Passed
74 |  |  | Products | Verifying that navigation of products from products section directs the user to products page | Should be directed the user to the product page | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click a product from products section |  |  | Passed
75 |  |  |  | Verifying that show more button works properly of the products section | Should work as per expectation | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Click show more button |  |  | Passed
76 |  | UI Testing | Slider | Verify that the slider automatically moves according to the specified behavior or settings | Slider should move automatically as per the requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the slider movement |  |  | Passed
77 |  |  |  | Check the speed and smoothness of the automatic movement | Should as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the slider's speed |  |  | Passed
78 |  |  |  | Confirm that the direction changes occur as expected | Should as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the slider's changing direction |  |  | Passed
79 |  |  |  | Confirm that the slider stays within the defined time intervals for changes | Should stays within the defined time intervals | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the slider's changing time |  |  | Passed
80 |  |  |  | Checking that the looping behavior is smooth and predictable | Should as per expectations | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the slider's looping behavior |  |  | Passed
81 |  |  |  | Verify that the slider stays pause when the cursor placed over it | Should pause when cursor is placed over it+F96:G100FF96:G103 | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the slider's pauseness |  |  | Passed
82 |  |  | Upcoming campaign | Verify that the upcoming campaign section is visible after its scheduled launch date and time | Should as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the upcoming campaign section |  |  | Passed
83 |  |  |  | Verifying the font, text color and style | Should be placed as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the fonts, text and style |  |  | Passed
84 |  |  |  | Validate that the details provided upcoming campaign such as discounts, offers,campaign duration are accurate | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the upcoming campaign section |  |  | Passed
85 |  |  |  | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the upcoming campaign section's spelling and grammar |  |  | Passed
86 |  |  |  | Checking that scrolling works perfectly for upcoming campaign | Should work perfectly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Scroll the mouse in the upcoming campaign section |  |  | Passed
87 |  |  | Deals of the Day | Verify that the deals of the day section is prominently visible on the Evaly's homepage | The section is visually appealing, well organized and easily accessible to users | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the deals of the section |  |  | Passed
88 |  |  |  | Verifying the font, text color and style | Should be placed as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the fonts, text and style |  |  | Passed
89 |  |  |  | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the deals of the section's spelling and grammar |  |  | Passed
90 |  |  |  | Validate that the images and thumbnails associated with each deal are of high quality and accurately represent the product | Should as per expectations | Images should load quickly and they accurate depict the product being offered | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the deals of the section |  |  | Passed
91 |  |  |  | Checking that deals of the day's product changes according to requirements | Should change according to the requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the deals of the section |  |  | Passed
92 |  |  |  | Checking there appears a tooltip when the cursor hover over a product | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the deals of the section 3.Place cursor over a product |  |  | Passed
93 |  |  | Flash Sale Products | Verify that Flash sale animated perfctly | Should be animated perfectly | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check Flash Sale section |  |  | Passed
94 |  |  |  | Verifying the font, text color and style | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check the text, fonts and style |  |  | Passed
95 |  |  |  | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check Flash Sale section |  |  | Passed
96 |  |  |  | Validate that the images and thumbnails associated with each product are of high quality and accurately represent the product | Should found as per requirements | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check Flash Sale section |  |  | Passed
97 |  |  |  | Check that show more button placed correctly | Should be placed as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check Flash Sale section 3. Check show more button's position |  |  | Passed
98 |  |  |  | Checking that tootip works perfectly when mosue hover over a product | Should present as per requirements | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check Flash Sale section 3. Place cursor over a product |  |  | Passed
99 |  |  | Shops | Verify that the Shops section is prominently visible on the Evaly's homepage | The section is visually appealing, well organized and easily accessible to users | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check Shops section |  |  | Passed
100 |  |  |  | Validate that the images and thumbnails associated with each shop are high quality and represent the shops correctly | Should found as per requirements | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2.Check Shops section |  |  | Passed
101 |  |  |  | Check that show more button placed correctly | Should be placed as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Shops section 3. Check the show more button's position |  |  | Passed
102 |  |  |  | Verifying the font, text color and style | Should be present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check fonts, text and style |  |  | Passed
103 |  |  |  | Verify that spellings and grammars of the Shops section | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Shops section's spelling and grammars |  |  | Passed
104 |  |  | Trending Now | Verify that the Trending Now section is prominently visible on the Evaly's homepage | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Trending Now |  |  | Passed
105 |  |  |  | Validate that the images and thumbnails associated with each Trending Now are high quality and represent the products correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Trending Now |  |  | Passed
106 |  |  |  | Checking there appears a tooltip when the cursor hover over a product | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Trending Now 3. Place mouse over a product and check it |  |  | Passed
107 |  |  |  | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Trending Now's spellings and grammars |  |  | Passed
108 |  |  |  | Verifying the font, text color and style | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Trending Now's text, fonts and style |  |  | Passed
109 |  |  | Popular Products | Verify that spellings and grammars of the Popular Products section | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Popular Products section's spelling and grammar |  |  | Passed
110 |  |  |  | Verify that the Popular Products section is prominently visible on the Evaly's homepage | Should visible as per reqirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Popular Products section |  |  | Passed
111 |  |  |  | Verifying the font, text color and style | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Popular Products section's font, text and style |  |  | Passed
112 |  |  |  | Validate that the images and thumbnails associated with each Popular products are high quality and represent the products correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Popular Products section |  |  | Passed
113 |  |  |  | Checking that a card pop up when cursor placed over the stars | Should appear a card when cursor hover over the star | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Popoular Products section |  |  | Passed
114 |  |  |  | Checking there appears a tooltip when the cursor hover over a product | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Popular Products section 3. Place mouse over a product's name |  |  | Passed
115 |  |  | Top Rated Shops | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Top Rated Shop's spellings and grammars |  |  | Passed
116 |  |  |  | Verifying the font, text color and style | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Top Rated Shop's text, fonts and style |  |  | Passed
117 |  |  |  | Validate that the images and thumbnails associated with each Top Rated Shops are high quality and represent the products correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Top Rated Shops section |  |  | Passed
118 |  |  |  | Verify that the Top Rated Shops section is prominently visible on the Evaly's homepage | Should visible as per reqirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Top Rated Shops section |  |  | Passed
119 |  |  |  | Checking that a card pop up when cursor placed over the stars | Should appear a card when cursor hover over the star | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Top Rated Shops section |  |  | Passed
120 |  |  | COD | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check COD section's spellings and grammars |  |  | Passed
121 |  |  |  | Verifying the font, text color and style | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check COD section's text, fonts and style |  |  | Passed
122 |  |  |  | Validate that the images and thumbnails associated with each COD section's Shops are high quality and represent the products correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check COD section |  |  | Passed
123 |  |  |  | Checking show more button placed correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check COD section 3. Check show more button |  |  | Passed
124 |  |  | B2B | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check B2B section's spellings and grammars |  |  | Passed
125 |  |  |  | Verifying the font, text color and style | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check B2B section's text, fonts and style |  |  | Passed
126 |  |  |  | Validate that the images and thumbnails associated with each B2B section's Shops are high quality and represent the products correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check B2B section |  |  | Passed
127 |  |  |  | Checking show more button placed correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check B2B section 3. Check show more button |  |  | Passed
128 |  |  | Products | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check products section's spellings and grammars |  |  | Passed
129 |  |  |  | Verifying the font, text color and style | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check products section's text, fonts and style |  |  | Passed
130 |  |  |  | Validate that the images and thumbnails associated with each product of products section's products are high quality and represent the products correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Products section |  |  | Passed
131 |  |  |  | Checking show more button placed correctly | Should found as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Products section 3. Check show more button |  |  | Passed
132 |  |  |  | Checking there appears a tooltip when the cursor hover over a product | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Products section 3. Place mouse over a product |  |  | Passed
133 |  |  |  | Checking "New" tag is present for all the products displayed in the Products section | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check Products section |  |  | Passed
134 | Footer | UI Testing |  | Checking spelling or grammatical mistakes | Should not present any spelling or grammatical mistakes | Found as per expectations | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check footer section |  |  | Passed
135 |  |  |  | Verifying the font, text color and style | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check footer section's text, fonts and style |  |  | Passed
136 |  |  |  | Verifying alignments | Should present as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check footer section's alignment |  |  | Passed
137 |  |  |  | Checking all the social media icons placed correctly | Should placed as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check footer section's social media icons |  |  | Passed
138 |  |  |  | Checking the google play icon placed correctly | Should placed as per requirements | Found as per requirements | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Check footer section's google play icon |  |  | Passed
139 |  | Functional Testing |  | Checking all the social media icons direct the user to the desired page | Should direct the user to the correct page | Found as per expectation | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Click on the social media icons individually |  |  | Passed
140 |  |  |  | Check that the Google Play directs to the correct website by clicking over it | Should direct the user to the correct website | Found as per expectation | N/A | 1. Go to the URL https://evaly.com.bd/ 2. Click on the Google Play icon |  |  | Passed

## Test Summary
Test Case Report | [6 empty] | Result :
Project Name | Evaly (Online Shopping Platform)
Module Name | User Management & Home Page |  |  |  |  | Total No. | Status
Feature Name | Sign Up, Sign In & Home
Test Case Version | 1 |  |  |  |  | 127 | PASS
Written By | Humaira Gulshan Putul |  |  |  |  | 14 | FAIL
Executed By | Humaira Gulshan Putul |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 127 | 14 | 0 | 0 | 141
Grand Total | 127 | 14 | 0 | 0 | 141
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Report
#SL 01 Issue: Capitalization issue Reproducing Steps: 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check the above text of the input fields(n should be N and p should be P of the Full Name and Confirm Password) Env: Production Module: Sign Up Priority: P5 Severity: Minor
Screenshot:SS\n_p_should_be_N_P.PNG
Responsible QA: Humaira
Bug Report
#SL 02 Issue: Missing Red asterisk of required fields Reproducing Steps: 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check red asterisk beside mandatory fields Env: Production Module: Sign Up Priority: P4 Severity: Minor
Screenshot: Red asterisk Missing
Responsible QA: Humaira
Bug Report
#SL 03 Issue: Taking blank spaces for Full Name Reproducing Steps: 1. Goto the URL https://evaly.com.bd/auth/signup 2.Put blank spaces in the Full name field Env: Production Module: Sign Up Priority: P4 Severity: Minor
Screenshort :SS\Blank_Spaces.PNG
Responsible QA: Humaira
Bug Report
#SL 04 Issue : Taking special characters as Full Name Reproducing steps : 1. Goto the URL https://evaly.com.bd/auth/signup 2.Input Special characters in the name field ENV: Production Module: Sign Up Priority: P4 Severity: Medium
Screenshot: SS\Special_Char.PNG
Responsible QA: Humaira

## Copy of Bug Report
Bug Report
#SL 01 Issue: Capitalization issue Reproducing Steps: 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check the above text of the input fields(n should be N and p should be P of the Full Name and Confirm Password) Env: Production Module: Sign Up Priority: P5 Severity: Minor
Screenshot:SS\n_p_should_be_N_P.PNG
Responsible QA: Humaira
Bug Report
#SL 02 Issue: Missing Red asterisk of required fields Reproducing Steps: 1. Goto the URL https://evaly.com.bd/auth/signup 2.Check red asterisk beside mandatory fields Env: Production Module: Sign Up Priority: P4 Severity: Minor
Screenshot: Red asterisk Missing
Responsible QA: Humaira
Bug Report
#SL 03 Issue: Taking blank spaces for Full Name Reproducing Steps: 1. Goto the URL https://evaly.com.bd/auth/signup 2.Put blank spaces in the Full name field Env: Production Module: Sign Up Priority: P4 Severity: Minor
Screenshort :SS\Blank_Spaces.PNG
Responsible QA: Humaira
Bug Report
#SL 04 Issue : Taking special characters as Full Name Reproducing steps : 1. Goto the URL https://evaly.com.bd/auth/signup 2.Input Special characters in the name field ENV: Production Module: Sign Up Priority: P4 Severity: Medium
Screenshot: SS\Special_Char.PNG
Responsible QA: Humaira

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (141/141)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/141)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (127/141)*100 = 90%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (14/141)*100 = 10%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/141)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A